## Sheet1
|  | Purpose: | This set of tests is intended to check functionality of the game and also functionality of Microsoft Kinect and
In App Game Play
Requirement ID | Sprint | Test Case Ref | Test Case Name | Descriptions | Search Parameters / Instructions | Checks | Expected Result | Actual Result | Results Pass/Fail
1 | 1 | TC.001 | Backgroud Image Dislay | GUI | 1. Launch Game | 1. Background image is displayed covering the screen 2. The title of the game is across the top of the screen | The background image is covering the screen The title is displayed across the top of the screen |  | Pass
2 | 1 | TC.003 | Play Button | GUI | 1. Launch Game 2. Select Play | Once player says "Play", "Start", or "Start Game" the game will begin with the speech recognition | The speech recognition will accept only certain words to begin the game |  | Pass
3 | 1 | TC.004 | Play Button | GUI | 1. Launch Game 2.Click Play Button | The user can click the play button | The user should be able to play the game by clicking on the Play Button |  | Pass
4 | 1 | TC.005 | Kinect Camera | GUI | 1. Launch Game 2. Test out game play | Kinect Camera picks up player. | Kinect Camera picks up player |  | Pass
5 | 1 | TC.006 | Movement of spaceman | GUI | 1. Launch Game 2. Movement Left | Player moves Left, and Kinect camera registers movement and spaceman moves left on screen | When the player moves left, the spaceman moves left from Kinect input |  | Pass
6 | 1 | TC.007 | Movement of spaceman | GUI | 1. Launch App 2. Movement Right | Player moves right, and Kinect camera registers movement and spaceman moves right on screen | When the player moves right, the spaceman moves right from Kinect input |  | Pass
7 | 1 | TC.008 | Asteroids fall downwards | GUI | 1. Launch Game | Asteroids falling downwards when game has started | The asteroids should fall downwards automatically when the game starts |  | Pass
8 | 1 | TC.009 | Game Over | GUI | 1. Launch Game 2. Test out Game play 3. Lose the game | Game over | The game should be over if an asteroid hits the player three times |  | Pass
9 | 1 | TC.010 | Game Over | GUI | 1. Launch Game 2. Test out Game play 3. Lose the game | Game Over | The player can use voice recognition to restart or quit the game from here |  | Pass
10 | 1 | TC.011 | Level 2 | GUI | 1. Launch Game 2. Test out the Game 3. Level 2 | After 120 seconds of player surviving, they will progress to level 2 | The player will progress to level 2 once they can live for over 120 seconds |  | Pass